## Slide 1: INCEPTION WORKSHOP
PROJECT PRESENTATION
“CONSERVING AQUATIC BIODIVERSITY IN AFRICAN BLUE ECONOMY”
By
Dr Mohamed Seisay,
Fisheries Management Expert, AU-IBAR
8-10 December 2021

## Slide 2: BASIC PROJECT INFORMATION
Title | CONSERVING AQUATIC BIODIVERSITY IN AFRICAN BLUE ECONOMY
Implementing Agency | African Union- Interafrican Bureau for Animal Resources (AU-IBAR); speculated technical office of DARBE of the African Union Commission
Funding Agency | Swedish International Development Cooperation Agency (SIDA)
Duration | 3 years; started 15th October 2021
Budget | USD 5,496,119
Collaborating partners and beneficiaries | AU member states, Specialized regional institutions (Regional Economic communities, Regional Sea Conventions, Environmental-based organizations, LME-based institutions, regional fisheries organizations, water-basin commission), Swedish Agency for Marine and Water Management, Universities, Research institutes, NGO-based organizations, Non-State actors
Coverage | 55 AU member states; 8 RECs in the five regions of Africa (West, Central, East, Southern and North)

## Slide 3: BASIC PROJECT INFORMATION
Project staff members:
Project Coordinator (Sustainable Blue Economy Expert)
Aquatic Biodiversity Specialist
Aquatic Ecosystems Management Expert (Consultant)
Gender Policy and Strategy Expert – Aquatic Environmental Management
Legal, Institutional Officer - Natural Resources and Environmental la

## Slide 4: OBJECTIVES
Overall objective => is to enhance the policy environment, regulatory frameworks and institutional capacities of AU member states and regional economic communities to sustainably utilize and conserve aquatic biodiversity and ecosystems
Strategic objectives =>
Ratify and/or align relevant international/regional instruments related to blue economy themes (with specific reference to protecting and conserving biodiversity)
Optimizing conservation and sustainable use of biodiversity while minimizing conflicts among blue economy sub-themes
Strengthening measures for mitigating the negative impacts of coastal and marine tourism, oil, gas, deep sea mining and climate change on aquatic biodiversity and environment
Strengthening gender inclusivity in aquatic biodiversity conservation and environmental management

## Slide 5: STRATEGIC OBJECTIVE 1
RATIFY AND/OR ALIGN RELEVANT INTERNATIONAL/REGIONAL INSTRUMENTS RELATED TO BLUE ECONOMY THEMES

## Slide 6: SO 1: OUTPUTS AND ACTIVITIES
OUTPUTS | ACTIVITY | SUB-ACTIVITIES
Output 1.1 Mechanisms for active participation of MSs in regional and global initiatives related to aquatic biodiversity and environmental regimes (ABNJ, CITES, COP meetings relating to CC, BRS, etc) developed. | 1.1.1. Enhancing effective role and participation in continental and global aquatic biodiversity and environmental related regimes | 1.1.1.1. Undertake studies and develop a mechanism for enhancing effective role and participation in regional and global biodiversity and environmental related regimes.
 |  | 1.1.1.2. Organize continental validation and awareness enhancing workshop among stakeholders on the relevant provisions, challenges and mechanisms for effective role and participation in these global regimes.
 |  | 1.1.1.3. Conduct a workshop for identified negotiators to technically support AU MSs in global negotiations e.g. CC COP meetings, CITES
 |  | 1.1.1.4. Support the participation of 5 AU MSs in relevant aquatic biodiversity and environmental fora
Output 1.2. Ratification and implementation of conventions and agreements related to conservation of biodiversity in AU MSs and RECs supported | 1.2.1. Identify continental and global biodiversity and environmental instruments relevant to sustainable management of Africa blue economy resources. | 1.2.1.1. Conduct assessment of relevant continental and global biodiversity and environmental instruments to develop priority actions for enhanced ratification and implementation.
 |  | 1.2.1.2. Conduct two virtual validation and regional awareness enhancing workshops on identified documents including key provisions and benefits.
 |  | 1.2.1.3. Support 10 AU member states to review national policies, regulations and align national instruments with relevant regional and global biodiversity and environmental instruments.
 |  | 1.2.1.4. Conduct national level validation workshops to validate the reviewed policies

## Slide 7: STRATEGIC OBJECTIVE 2
OPTIMIZING CONSERVATION AND SUSTAINABLE BIODIVERSITY WHILE MINIMIZING CONFLICTS AMONG USERS OF BLUE ECONOMY RESOURCES.

## Slide 8: SO 2: OUTPUTS AND ACTIVITIES
OUTPUTS | ACTIVITY | SUB-ACTIVITIES
Output 2.1: Enforceable Regulatory frameworks for effective and sustainable regional MCS systems developed. | 2.1.1 Enhancing Sustainable Monitoring Control and Surveillance (MCS) Systems for conservation and protection of biodiversity: | 2.1.1.1. Conduct a study to assess the status of MCS for combating unsustainable practices of fishing and other blue economy resources in AU member states and regional economic communities and develop mechanism to strengthen MCS; identifying capacity and weaknesses
 | 2.1.2. Support the establishment of cost-effective and sustainable financial arrangements for effective regional cooperation on MCS and enforcement in selected regions | 2.1.2.1 Develop framework for establishing functional financial and sustainable regional MCS systems
 |  | 2.1.2.2. Organize two virtual regional workshops to validate findings and recommendations of the studies in 2.1.1.1. and 2.1.2.1.
 |  | 2.1.2.3. Pilot and operationalize the recommendations (in 2.1.1.1. and 2.1.2.1.) in 2 regional institutions;
 |  | 2.1.2.4 Support to implementation of cost-effective sustainable financial systems.

## Slide 9: SO 2: OUTPUTS AND ACTIVITIES
OUTPUTS | ACTIVITY | SUB-ACTIVITIES
Output 2.2. A framework for establishing national, regional and transboundry cooperation on Africa Blue Economy Strategy Thematic Areas established | 2.2.1. Establish regional cooperation on transboundary issues in shared aquatic ecosystems towards; formulating harmonized regional frameworks on aquatic biodiversity conservation. | 2.2.1.1. Conduct integrated assessment of two identified transboundary aquatic ecosystems to identify critical aquatic environmental issues affecting biodiversity and develop mechanisms for joint management plans and protocols in shared blue economy resources; towards developing harmonized regional frameworks for aquatic biodiversity conservation
 |  | 2.2.1.2. Conduct two virtual validation and awareness enhancing workshops on critical environmental issues in 2 transboundary ecosystems and the draft harmonized regional frameworks for aquatic biodiversity conservation
 |  | 2.2.1.3. Support to provide technical assistance to five AU Member states to rollout the joint management plans and protocols and the harmonized regional frameworks for conserving aquatic biodiversity;
 | 2.2.2. Formulate mechanisms to institutionalize Marine Spatial Planning (MSP) at national and regional levels | 2.2.2.1. Conduct an assessment to map MSPs in Africa, document lessons, best practices and develop guidelines for their institutionalisation at national and regional levels.; current management strategies and identification of elements pertinent for the regional MSP
 |  | 2.2.2.2. Convene two virtual regional Think Tank meetings on MSP implementation and governance to validate the findings of the consultants
 |  | 2.2.2.3 Support to specialized regional institutions to strengthen identified transboundary MSPs;

## Slide 10: SO 2: OUTPUTS AND ACTIVITIES
OUTPUTS | ACTIVITY | SUB-ACTIVITIES
Output 2.3. Capacities for restoring and conserving threatened aquatic biodiversity and environment strengthened. | 2.3.1 Support rehabilitation of depleted aquatic biodiversity and habitats | 2.3.1.1. Conduct a continental review of existing Marine Protected Areas (MPAs), document lessons, best practices and formulate guidelines for their sustainable implementation and governance.
 |  | 2.3.1.2. Convene two virtual regional Think Tank meetings on MPA implementation and governance to validate the findings of the consultancies 2.3.1.1
 |  | 2.3.13. Based on the outcomes of the studies on review of existing MPA initiatives, the project would provide technical and direct support to two specialized regional institutions; to establish or strengthen climate resilient transboundary MPA
 | 2.3.2 Establish Continental Centres of Excellence for capacity building on aquatic biodiversity | 2.3.2.1. Support the establishment of two continental Centres of Excellence on aquatic biodiversity; This activity is supporting the implementation of 2014 Ministerial Decision to identify Centres of Excellence in relevant aquatic fields including biodiversity
 |  | 2.3.2.2. Strengthen capacity of two identified Centres of Excellence - based on identified gaps (equipment and training materials);

## Slide 11: STRATEGIC OBJECTIVE 3
Strengthening measures for mitigating the negative impacts of coastal and marine tourism, oil, gas, deep sea mining and climate change on aquatic biodiversity and environment.

## Slide 12: SO 3: OUTPUTS AND ACTIVITIES
OUTPUTS | ACTIVITY | SUB-ACTIVITIES
Output 3.1 Measures for minimizing the negative impacts of climate change on biodiversity and environment strengthened and implemented | 3.1.1. Mitigate the impact of climate change on aquatic biodiversity | 3.1.1.1. Conduct studies on the negative impact of climate change on aquatic biodiversity and environment and recommend mitigation strategies
 |  | 3.1.1.2. Conduct a virtual continental validation workshop on the studies on impact of climate change on aquatic biodiversity, their environment and develop recommendations
 |  | 3.1.1.3 The project would support to strengthen conservation and climate change impact mitigation efforts for identified ongoing initiatives on ecosystems restoration (mangroves, sea grass) on mitigation of climate change impact (increasing carbon sink); also including projects on conservation of coral reefs
OUTPUT 3.2. Strategies for an integrated strategic framework for sustainable coastal and marine tourism and mining developed | 3.2.1. Identify priority issues and actions for sustainable coastal and marine tourism and mining activities on aquatic biodiversity and environment and develop guidelines. | 3.2.1.1. Conduct studies to identify priority issues and actions for sustainable coastal, marine tourism and mining activities for aquatic biodiversity conservation and environment protection
 |  | 3.2.1.2. The studies would be followed by five national stakeholder’s consultation to develop national master plans on sustainable coastal and marine tourism and mining development for biodiversity conservation and environmental protection; the private sector would be part of the sector holder's workshop.
 |  | The project would conduct studies on impact of coastal and marine tourism development as well as mining activities on the biodiversity conservation and environmental protection. The studies would be followed by five national stakeholder’s consultation to develop national master plans on coastal and marine tourism and mining development with reference to biodiversity conservation and environmental protection
 |  | 3.2.1.3. Based on the identified priority issues in the national master plan, the project would support development or (strengthening), monitoring and regulatory frameworks in 5 AU member states for sustainable coastal and marine tourisms and mining for biodiversity conservation and environmental protection

## Slide 13: STRATEGIC OBJECTIVE 4
Strengthening gender inclusivity in aquatic biodiversity conservation and environmental management

## Slide 14: SO 4: OUTPUTS AND ACTIVITIES
OUTPUTS | ACTIVITY | SUB-ACTIVITIES
Output 4.1 Continental strategy for gender inclusivity in aquatic biodiversity and environmental management developed | 4.1.1. Support development of a continental strategy for inclusion of gender in aquatic biodiversity and environmental management | 4.1.1.1. Convene an Expert Consultative meeting to identify priority issues and actions for enhancing the role of women in aquatic biodiversity and environmental management; hire facilitator
 |  | 4.1.1.2. Convene a virtual continental think tank stakeholders consultation workshop on identified priority issues and actions for enhancing the role of women in biodiversity and environmental management
 |  | 4.1.1.3. Technical support would be given to selected AU MS to develop all inclusive and deliberate biodiversity strategies as important entry points for women’s empowerment; for enhancing the role of women and youth in inclusive aquatic biodiversity and integrated environmental management ; .opportunities to build on women’s specific roles and capacities in biodiversity and environmental management
 |  | 4.1.1.4. Mapping of ongoing environmental based-NGOs focusing on conserving biodiversity and environment protection would be conducted and technical support provided by the project to develop ot strengthen gender-sensitive workplans to enhance the role of women and youth in biodiversity protection and environmental governance (NGOs include Non-State Actors, CSOs, Private sector involved in environmental management)

## Slide 15
Highlighting the role of RECs and Specialized Regional Institutions in supporting project implementation

## Slide 16: IMPLEMENTATION MECHANISMS
The RECs will be both beneficiaries as well as partners in the implementation.
The capacity of the RECs will be strengthened in aquatic biodiversity conservation, environmental management, climate resilience, sustainable coastal tourism and infrastructure development etc.
The RECs will act as an interface or conduit in delivery support to the AU member states.
In view of their role in facilitating regional integration, the identified activities shall be undertaken with the involvement of the RECs, including implementation of activities on Marine Spatial Planning, regional environmental monitoring programmes, regional strategies on coastal tourism, climate smart and resilient coastal infrastructure, regional strategies on women empowerment and effective engagement in biodiversity and ecosystem conservation

## Slide 17: REGIONAL INSTITUTIONS
The project would work through regional economic communities that have the mandate for regional integrations.
Eight recognized regional communities by African Union:
  Arab Maghreb Union (UMA)
  Common Market for Eastern and Southern Africa (COMESA)
  Community of Sahel–Saharan States (CEN–SAD)
  East African Community (EAC)
  Economic Community of Central African States (ECCAS)
  Economic Community of West African States (ECOWAS)
  Intergovernmental Authority on Development (IGAD)
  Southern African Development Community (SADC)

## Slide 18: Specialized Regional Institutions
Lake Victoria Fisheries Organization (LVFO)
Lake Tanganyika Authority (LTA)
Lake Chad Basin Commission (LCBC)
Sub Regional Fisheries Commission (SRFC)
Regional Fisheries Commission for the Gulf of Guinea(COREP)
The Nairobi Convention
The Abidjan Convention
The Fisheries Committee for West Central Gulf of Guinea (FCWC)
There are also environmental based NGOs supporting conservation efforts in various regions of the continent. The project would collaborate with these various organizations for the implementation of project activities especially at regional levels.

## Slide 19: AREAS OF COLLABORATION
MAINLY ON TRANSBOUNDARY ISSUES
The support to RECs would go towards strengthening regional (2) MCS Centres or initiatives
Strategy for sustainable (cost-effective) financing of MCS and support to implementation of the strategy
Regional frameworks for aquatic biodiversity in transboundary context
Support to strengthening and/or establishing identified Transboundary MSP initiative
Support to strengthening and/or establishing identified Transboundary MPA initiative
Regional mechanism and guidelines (e.g. coastal and marine tourisms;
Gender inclusivity

## Slide 20: Terms of reference for working groups

## Slide 21: WORKING GROUPS
WORKING GROUP 1
Ratify and/or align relevant international/regional instruments related to blue economy themes (with specific reference to protecting and conserving biodiversity)
WORKING GROUP 2
Optimizing conservation and sustainable use of biodiversity while minimizing conflicts among blue economy sub-themes
WORKING GROUP 3
Strengthening measures for mitigating the negative impacts of coastal and marine tourism, oil, gas, deep sea mining and climate change on aquatic biodiversity and environment
WORKING GROUP 4
Strengthening gender inclusivity in aquatic biodiversity conservation and environmental management

## Slide 22: WG 1: Ratify and/or align relevant international/regional instruments related to blue economy themes (with specific reference to protecting and conserving biodiversity)
1 | ESWATINI | ISAAC GCINA DLADLA
2 | SOMALI | MUKASA TOM BUKENYA
3 | UGANDA | MUKASA TOM BUKENYA
4 | S SUDAN | DAVID BATALI OLIVER
5 | MALAWI | FRIDAY NYAYA
6 | NIGERIA | OBENWA OLADIPO
7 | ETHIOPIA | ASEFA CHIMDI SEDETO
8 | TANZANIA | EMMANUEL BULAYI
9 | KENYA | RODRICK KUNDU
10 | COMESA | YOSEPH MAMO
11 | LVFO | 
12 | IGAD | ESHETE DEJEN
13 | EARFISH | SILVANO NAMADOA

## Slide 23: WG 2: Optimizing conservation and sustainable use of biodiversity while minimizing conflicts among blue economy sub-themes
1 | ESWATINI | PHUMZILE MHLANGA
2 | SOMALI | YONIS ADAN
3 | S SUDAN | JACKSON MOGGA
4 | MALAWI | GEORGE KANYERERE
5 | ETHIOPIA | ADDISU NEGASH MELKIE
6 | KENYA | ROBERT KAMAU KAMITI
7 | COMESA | 
8 | LVFO | EDWARD RUKUUNYA
9 | IGAD | ESHETE DEGEN
10 | EARFISH | SLVANO NAMADOA

## Slide 24: WG 3: Strengthening measures for mitigating the negative impacts of coastal and marine tourism, oil, gas, deep sea mining and climate change on aquatic biodiversity and environment
1 | BENIN | ELAINE ZEKPTE
2 | RCA | MOLEKPO GILBERT
3 | NIGER | COL MALICK IBRAHIM ABDOU
4 | COTE D'IVOIRE | DELEUSE SERGE DONALD
5 | DJIBOUTI | MOHAMED ELMI
6 | MALI | NOUHOUM BERTHE
7 | TUNISIA | ASMA BEN ABDALLAH
8 | BURKINA FASO | SAWADOGO PHILIPPE
9 | SENEGAL | LT COL SERIGNE ABDOU AZIZ SY NDIAYE
10 | TOGO | ABDEL-GANIOU SOULEMANE
11 | GABON | MVE BEH JEAN HERVÉ
12 |  | LANDRY STEGE
13 | LCBC | AMINU MAGAJI BALA
14 | PRIVATE SECTOR | BOUBACAR DIALLO

## Slide 25: WG 4: Strengthening gender inclusivity in aquatic biodiversity conservation and environmental management
1 | RCA | PIERRE SEMBENE
2 | COTE D'IVOIRE | ERNEST KOUAKOU
3 | DJIBOUTI | ADAN ARBAHIM HASSAN
4 | GABON | DIRECTEUR DE LA PECH
5 | UMA | FAOUZIA CHAKIRI
6 | NAFRRI | WINNIE NKALUBO
7 | ABIDJAN CONVENTION | BANA PAULE – MYRIAM CHARLOTTE
8 | WIMAFRICAN | ROLLENS MACFOY
9 |  | YVONNE MOYU'TAGNE
10 | AFEMISH | CHIAMAKA MOGO
11 | AWFISHNET | BEYENE ATEBA

## Slide 26: Thank You
AU-IBAR: Providing leadership in the
development of animal resources for Africa