## Slide 1: SECOND DIALOGUE AND SENSITIZATION MEETING WITH RECS ON EMERGING ISSUES FROM IMPLEMENTATION OF FISHGOV 2
PRESENTATION
Enhancing sustainable fisheries management and aquaculture development in Africa: A programme for accelerated reform of the sector (FishGov 2)
15-16 June 2022
ABUJA, NIGERIA

## Slide 2: FISHGOV 2- PROJECT INFORMATION
BUDGET: EUR 12,000,000 EU contribution
EUR 1,200,000 AU Contribution
DURATION: 54 Months, started 1st January 2021
COVERAGE: 55 AU MS and 8 RECs
IMPLEMENTATION PARTNERS: AU-IBAR (contracting authority and lead coordinating agency) and AUDA-NEPAD
PROJECT TECHNICAL STAFF:
Senior Fisheries Officer at AU-IBAR (Coordinator)
Fisheries and aquaculture resources management expert at AU-IBAR
Fish Trade and Investment Officer at AU-IBAR
Senior Policy Officer – DARBE
Programme Officer- Fisheries and Aquaculture – AUDA-NEPAD
Progarmme Assistant – Fisheries and Aquaculture - AUDA-NEPAD

## Slide 3: OBJECTIVES
The overall objective of the project is to improve food security, livelihoods and wealth creation in sustainable fisheries and aquaculture, aligned with AU Agenda 2063 within the framework of PFRS.
The specific objectives are the following:
African Union decisions on sustainable fisheries and aquaculture policies are evidence based
Fisheries and aquaculture policies in Africa are coherent with the PFRS and other AU priorities and coordinated at continental, regional and national levels
Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates and effectively implements relevant global instruments

## Slide 4: RESULT 1: AFRICAN UNION DECISIONS ON SUSTAINABLE FISHERIES AND AQUACULTURE POLICIES ARE EVIDENCE BASED
Output 1.1 AU stakeholders have access to quality knowledge products on African fisheries and aquaculture
Output 1.2 Existing platforms and networks are reviewed, rationalized and operationalized for effective participation of stakeholders in policy development and implementation
Output 1.3 A solid reporting system to STC on the implementation of the PFRS is put in place and integrated to CAADP process
Output 1.4 Mechanisms are developed to ensure that sustainable fisheries and aquaculture are mainstreamed in the development of AU policies / initiatives affecting the sector
Output 1.5 Advocacy is improved and awareness created about the importance of sustainable fisheries and aquaculture

## Slide 5: RESULT 2: FISHERIES AND AQUACULTURE POLICIES IN AFRICA ARE COHERENT WITH THE PFRS AND COORDINATED AT CONTINENTAL, REGIONAL AND NATIONAL LEVELS
Output 2.1 Capacities and systems for regional collaboration and integration regarding shared fisheries and aquaculture resources management are improved and linkages with environmental governance frameworks are enhanced
Output 2.2 Capacities of Member States, RECs and RFBs to develop realistic sustainable fisheries and aquaculture policies in coherence with the PFRS are strengthened
Output 2.3 Capacities are strengthened to facilitate intra and inter regional fish trade in line with the regional integration trade agenda and the Protocol on Trade in Goods of the Africa Continental Free Trade Area

## Slide 6: RESULT 3: AFRICA IS ADEQUATELY REPRESENTED AND EFFECTIVELY PARTICIPATES IN INTERNATIONAL FISHERIES AND AQUACULTURE FORA AND ABLY DOMESTICATES RELEVANT GLOBAL INSTRUMENTS
Output 3.1 Capacities of AU Member States – including SIDS - in terms of international negotiations are increased and a mechanism is put in place to coordinate African common positions
Output 3.2 Mechanisms are put in place to encourage and facilitate the domestication of global instruments and initiatives at continental, regional and national levels
Output 3.3 Capacities of AU Member States are strengthened to effectively articulate African positions on fisheries and aquaculture in the AU-EU dialogue

## Slide 7: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Activity |  |  |  |  | 
Project Technical Coordinating Committee meeting | Organize Project technical coordination meeting |  |  |  | 
Project Steering Committee meeting | Organize first project steering committee meeting |  |  |  | 
Inception | Organize project inception meeting |  |  |  | 
tOutput 1 1: AU stakeholders have access to quality knowledge products on African fisheries and aquaculture | 
1.1:1. Collect and centralize information and research relating to fisheries and aquaculture in Africa as a repository within AU institutions and establish a mechanism for regular updating; | 1.1.1.1. Develop and update database on fisheries and aquaculture and develop mechanism for data management.
 | 1.1.1.2. Commission studies on identifications of sources of fisheries, aquaculture, socio-economics and environmental related data (research and statistics) in 5 regions (West, central, East, South and North)
1.1.2. Conduct policy oriented studies to address social, economic and environmental challenges on fisheries and aquaculture in Africa (e.g. on the state of the stocks, economic valuation of aquatic and coastal goods and services, impact of climate change etc). | 1.1.2.1. Collect existing relevant information in AU MS and institutions on the state of fish stocks in 2 regions.
 | 1.1.2.2. Conduct economic valuation of ecosystem goods and services, impact of climate change on fisheries and aquaculture.
1.1.3. Update the AU-FAO study on the Value of African fisheries (2014); | 1.1.3.1. Develop methodology, template and training manuals for updating the AU-FAO study on the value of fisheries 2014.
1.1.4. Produce foresight studies and relevant fisheries and aquaculture contributions to ongoing thematic processes and initiatives (i.e. on food and nutrition security, gender, marine biodiversity and ecosystems, climate change, blue economy etc) | 1.1.4.1 Conduct foresight studies to inform policy reforms on relevant fisheries and aquaculture issues - diverse consultancies to address issues above.
1.1.5. Document lessons learnt and best practices for informed and rational interventions; | 1.1.5.1. Document lessons learnt and best practices on current and emerging fisheries and aquaculture related issues for informed and rational interventions.

## Slide 8: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.2 Existing platforms and networks are reviewed, rationalized and operationalized for effective participation of stakeholders in policy development and implementation | 
1.2.1. Conduct a functional review of existing platforms and networks in relation to PFRS and AFRM (e.g. AFRIPAAS, AWFISHNET, Policy Research Network etc); | 1.2.1.1. Review and propose mechanisms for rationalization of existing fisheries and aquaculture platforms and networks and propose a framework for anchorage with RECs and relevant RFOs.
1.2.2. Support rationalization of existing platforms and networks, ensure institutional anchorage at relevant level, enhance their capacities and use them to implement identified activities / pilot projects; | 1.2.1.1. Review and propose mechanisms for rationalization of existing fisheries and aquaculture platforms and networks and propose a framework for anchorage with RECs and relevant RFOs.
 | 1.2.2.2. Purchase equipment as may be required by COEs or other specialized institutions for effective implementation of activities related to the Action.
 | 1.2.2.3 Conduct assessment and review for selection of additional centres of excellence in relevant disciplines in fisheries and aquaculture; in line with 2019 STC ARDWE recommendations.
1.2.3 Develop cost effective mechanisms for stakeholder consultation. | 1.2.3.1 Commission a study to develop a cost effective mechanism for stakeholder's consultation and generate specific recommendations based on best practices.
1.2.4. Simplify and operationalize the AFRM. | 1.2.4.1. Organize a consultative workshop to revise TORs for the various organs of the AFRM in line with the third STC-ARDWE recommendation.

## Slide 9: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.3 A solid reporting system to STC on the implementation of the PFRS is put in place and integrated to CAADP process. | 
1.3.1. Develop indicators to monitor the implementation of PFRS in line with the Malabo goals. | 1.3.1.1 Develop and propose mechanisms for operationalization of a robust M&E systems based on PFRS guidelines for monitoring PFRS implementation.
1.3.2. Produce annual snapshot of fisheries and aquaculture performance reports based on these indicators | 1.3.2.1. Prepare and compile biennial status report that would contribute to the Africa fisheries and aquaculture report for year 1
1.3.4. Actively contribute to the agenda of STC meetings, based on strategic planning and support the organization of biennial African ministerial dialogue on Fisheries and aquaculture. | 1.3.4.2 Prepare documentations for 3 STCs and high level AU policy organs.
 | 1.3.4.3. Facilitate the participation of experts in STC expert session's meetings to develop recommendations for the STC-ARDWE.
 | 1.3.4.4. Facilitate the participation of relevant officials in STC ministerial sessions to, among others, review the experts' recommendations.
Output 1.4 Mechanisms are developed to ensure that sustainable fisheries and aquaculture are mainstreamed in the development of AU policies / initiatives affecting the sector. | 
1.4.1. Map initiatives that are underway or planned at the AU that are relevant to fisheries and aquaculture and contribute to their development / implementation by providing relevant input (of. discussions on blue economy, maritime security, environmental protection and ocean governance etc). Build synergies and support alignment among these different sectors; | 1.4.1.1. Organize internal virtual meeting among AUC Departments to map initiatives that are underway or planned at the AU which are relevant to fisheries and aquaculture, for synergistic implementation of activities that relevant to fisheries and aquaculture (e.g. blue economy, maritime security, environmental protection and ocean governance)
1.4.3. Associate relevant AU services to activities developed under this Action | 1.4.3.1. Organize internal virtual (and Physical meetings) to develop and operationalize a framework for internal coordination of fisheries and aquaculture among relevant AUC Actors

## Slide 10: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.1 Capacities and systems for regional collaboration and integration regarding shared fisheries and aquaculture resources management are improved and linkages with environmental governance frameworks are enhanced. | 
2.1.2. Ensure cross-regional/trans-regional coherence of RECs and RFBs strategies and facilitate their institutional anchorage, in line with the PFRS. | 2.1.2.1. Collect best practices and lessons learnt on functional institutional anchorage between RECs and RFBs/RSC and propose a framework for effective anchorage.
2.1.3. Identify mechanisms for establishing / strengthening linkages between regional organizations in charge of fisheries management (RFMOs/RFBs) and regional organizations in charge of environmental issues (RSC and inland water bodies). | 2.1.3.1. Develop a mechanism for establishing/strengthening linkages between specialized regional fisheries institutions and environmental agencies.
Output 2.2 Capacities of Member States, RECs and RFBs to develop realistic sustainable fisheries and aquaculture policies in coherence with the PFRS are strengthened. | 
2.2.1. Develop capacities and provide technical support to Member states and RECs to develop sectoral strategies and investment plans | 2.2.1.1. Conduct studies to establish which AU MS have sectoral strategies and investment plans and develop a mechanism for twinning between those with and those without – 2 regions
2.2.2. Support member States in reviewing their policies and legislations and aligning them with best international practices (i.e. the FAO code of conduct for responsible Fisheries, etc) and existing continental / regional instruments (e.g. PRFS, RFB/RSC recommendations etc) | 2,2,2,1 Review and align national fisheries and aquaculture polices and laws with the PFRS, regional instruments and global best practices for 15 AU member states
 | 2.2.2.2. Facilitate national validation workshop for reviewed national policies and laws at Member States’ level.
2.2.3. Mainstream sustainable and climate-resilient fisheries and aquaculture in NAIPS, RAIPs and other Investment programmes. | 2.2.3.1. Review national and regional fisheries-aquaculture plans to mainstream sustainable and climate-resilient, environmentally sustainable fisheries and aquaculture, in NAIPS, RAIPs and other Investment programmes.
 | 2.2.3.2 Conduct national consultative workshops to validate the outcomes of the above review in 15 AU member states
 | 2.2.3.3. Conduct regional consultative workshops to validate the outcomes of the above review (5 RECs).
2.2.4. Facilitate stakeholders consultation on the design and implementation of national and regional strategies | 2.2.4.1. Develop training materials and facilitate a training workshop on the design of fisheries and aquaculture strategies for implementation at national and regional levels.

## Slide 11: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.3 Capacities are strengthened to facilitate intra and inter regional fish trade in line with the regional integration trade agenda and the Protocol on Trade in Goods of the Africa Continental Free Trade Area | 
2.3.1. Identify strategic regional value chains for sustainable fisheries and aquaculture | 2.3.1.1 Hire 3 COEs to conduct studies in West_Central, East_Southern and Northern regions to identify strategic regional value chains for sustainable fisheries and aquaculture
2.3.3. Support regional approaches for the establishment of regional reference laboratories and diagnostic networks; | 2.3.3.1. Conduct institutional assessment of laboratories and diagnostics networks in the various regions of Africa and recommend mechanisms for establishing regional reference laboratories and diagnostic networks for fish and fish products. The consultancy should also entail assessment of capacities for other certification processes for enhanced market access.
2.3.4. Enhance the capacity of fisheries and aquaculture traders with due consideration for small scale traders and women engaged in fish trade an processing; | 2.3.4.1. Develop an advocacy strategy and mechanism for effective participation of women and youth fish traders in fisheries and aquaculture policy dialogue and networking.
 | 2.3.4.3. Organize national workshops to facilitate establishment of national chapters for Awfishnet in fragile states (15 AU MS) towards strengthening effective engagement in decision making at national levels on issues relating to fisheries and aquaculture.
2.3.5. Improve aquatic disease outbreak detection, notification and support coordinated response. | 2.3.5.1.Develop Guidelines to strengthen diagnostic capacities of competent national authorities and networks on aquatic animal disease detection, surveillance and coordinated responses, based on OIE Aquatic Animal Health Code and Manual of Diagnostic Tests for Aquatic Animals (this activity includes stakeholder's participation in a virtual meeting to validate the guidelines).

## Slide 12: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
Output 3.1 Capacities of AU Member States – including SIDS - in terms of international negotiations are increased and a mechanism is put in place to coordinate African common positions. | 
3.1.2. Identify specific needs of African SIDS and take them into account in strategic positions in international fora | 3.1.2.1. Identify specific issues relevant to SIDs and develop draft strategic positions and make specific recommendations for establishment/strengthening a platform of SIDS.
 | 3.1.2.2 Convene a virtual consultative workshop to validate draft strategic position and the recommendations for establishment of a platform of SIDs.
3.1.3. Identify expertise in the different Member States and set up a consultation mechanism to prepare positions; | 3.1.3.1.Prepare a roster of fishery and aquaculture experts in the different Member States and set up a consultation mechanism to draft positions and mobilize technical expertise
 | 3.1.3.2. Conduct a virtual workshop involving AU member states on identification of issues and formulation of common positions.
3.1.4. Increase capacities on international issues and organize specific trainings for pre-identified negotiators; | 3.1.4.1. Identify global issues and agendas which impact on national, regional and continental fisheries and aquaculture development.

## Slide 13: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 3.2 Mechanisms are put in place to encourage and facilitate the domestication of global instruments and initiatives at continental, regional and national levels | 
3.2.1. Identify a list of priority instruments and initiatives (e.g. PSMA, CCRF, SSF-VG, CITES, CBD etc) | 3.2.1.1. Identify and analyze priority instruments and initiatives and outline strategies for effective participation by AU member states.
3.2.2. Establish and regularly update their state of ratification and domestication | 3.2.2.1. Develop a mechanism for follow-up on implementation and ratification of relevant instruments by AU MS for biennial reporting progress of domestication, including instruments relating to combating IUU (eg PSMA, EU-IUU regulations).
 | 3.2.2.3. Convene a virtual consultative meeting with AU MS and RECs to validate.
 | 3.2.2.4. Conduct a review of national policies in 15 AU MS and make specific recommendations for alignment and domestication of global instruments.
3.2.3. Develop inputs for the STCs and high level AU policy organs | 3.2.3.1. Prepare meeting documents for STC and high level AU Policy Organs; STC meetings thrice in 4 years (AU-IBAR, AUDA-NEPAD, DREA).
 | 3.2.3.2. Organize internal meetings to prepare issues for presentation to STCs and other High Level Policy meetings: (AU-IBAR, DREA, OLC (AU office of Legal Counsel) and other relevant AUC departments and STC-ARDWE Bureau;
3.2.4. Support dialogue and sensitization at RECs level | 3.2.4.1 Convene regular dialogue meetings and sensitization with RECs on emerging issues of the Action.
3.3.1. Collect information on relevant EU initiatives (Alliance for Sustainable Investment and Jobs, EIP etc); | 3.3.1.1. Prepare materials on relevant EU initiatives and make appropriate recommendations to AU MS for articulation of coherent African positions during AU-EU dialogue.
3.3.2. Engage in a regular sectoral dialogue with European Commission services and identify issues of common interest; | 3.3.2.1. Organize virtual dialogue meetings with EU (once a year) to identify issues of common interest in fisheries and aquaculture.

## Slide 14: IMPLEMENTATION MECHANISM
The African Union Inter-African Bureau for Animal Resources (AU-IBAR) will be responsible for overall management and coordination of the Action.
The implementation partners of the Action will be AU-IBAR and AUDA-NEPAD;
A Sub-delegation agreement between AU-IBAR and AUDA-NEPAD will be signed in which details on the activities to be implemented by the AUDA-NEPAD will be provided
The Action shall establish a project coordinating committee, to ensure coherence in the implementation of activities by the implementing partners and other institutions. This committee shall be composed of Project implementing partners and will act as the project planning, monitoring and coordination platform and shall ordinarily meet twice a year.
A Project Steering Committee (PSC), shall be set up to oversee and validate the overall direction and policy of the project

## Slide 15: IMPLEMENTATION MECHANISM CON’T
The COEs or specialized (knowledge-based) institutions would be the preferred consultants. However, where there may be challenges in identifying appropriate COEs or specialized institutions for some specific limited consultancies, consideration would be given to proven individual experts that are qualified for these specific consultancies.
The RECs play an important role in facilitating regional integration in the continent. The project would leverage on their mandate to promote regional cooperation. In this regard, the project will work closely with the RECs to gain political commitments and facilitate the implementation of activities that are regional in nature
RFMOs and RFBs are intergovernmental bodies through which States cooperate on the management of fisheries in specific region. Especially the RFBs, bodies would be strengthened as beneficiaries as well as support implementation of selected project activities within their areas of competencies
Platforms and networks would be utilized as assets to support the implementation of certain activities of the project. The project would support the rationalization of these platforms and networks as well as utilize them in the implementation of selected activities

## Slide 16: SUSTAINABILITY MECHANISMS
The successful accomplishment of the project would result in evidence-based decision making with regards to fisheries and aquaculture by policy organs of the African Union. The source of high quality data would also be available to the stakeholders in the fisheries and aquaculture sector, including AU member states, RECs, RFBs etc for sustainable governance of the sector
Coordination and institutional collaboration would be enhanced and broadened between regional institutions to include RECS, RFBs, RSC and RFMOs, WBC. This would result in synergies in the governance of the sector especially at regional levels for sustainable management of shared fish stocks.
Improved governance of the fishery and aquaculture sectors would be ensured through fostering policy coherence, accountability as well as ratification and adoption of international best practices and global instruments by AU member states and RECs.
Sustainable exploitation of fish stocks and responsible aquaculture practices would improve through capacity building in fisheries management approaches or tools and aquaculture practices by provisions of policy briefs, advocacy notes, access to quality data and information and foresight studies.
Improved governance and management practices would impact on increased contribution of the sector to GDP, economic growth, food security and livelihoods and social welfare, food safety, including employment, in the long-time.
Participatory, inclusive approaches and transparency in the governance of the sector would be enhanced through active, effective and coordinated stakeholders (the NSAs platforms, AWFISHNET, MOSFA, ANAF, PRNFAA)
The visibility of the importance of the sector in national development, food security, and social cohesion would be increased and public sector support or allocation enhanced through establishment of the culture of engagement and consultation between the fisheries and aquaculture sector with other sectors such as finance, public health, trade, judiciary, foreign affairs ministries or departments at member states level. The increased public and private investments in the sector through increased visibility of the sector in national and regional investment plans
Increased recognition of African fisheries and aquaculture in global fora through effective coherent African voice
Enhanced partnership and coordination between African Union and European Union on sustainable fisheries and aquaculture development

## Slide 17: Thank You
AU-IBAR: Providing leadership in the development of animal resources for Africa