## Slide 1: SECOND DIALOGUE AND SENSITIZATION MEETING WITH RECS ON EMERGING ISSUES FROM IMPLEMENTATION OF FISHGOV 2
PRESENTATION
PROGRESS OF IMPLEMENTATION
Enhancing sustainable fisheries management and aquaculture development in Africa: A programme for accelerated reform of the sector (FishGov 2)
15-16 June 2022
ABUJA, NIGERIA

## Slide 2: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Activity |  | Progress of implementation
Project Technical Coordinating Committee meeting (PTCC) | Organize Project technical coordination meeting | Two PTCC meetings held; one in April 2021 (virtual) and one in December 2021 (physical)
Project Steering Committee meeting (PSC) | Organize first project steering committee meeting | First PSC meeting held in April 2021 (Virtual)
Inception meeting | Organize project inception meeting | Inception meeting held inn may 2021 (virtual)
Output | Activity | Progress of implementation
Output 1 1: AU stakeholders have access to quality knowledge products on African fisheries and aquaculture |  | 
1.1:1. Collect and centralize information and research relating to fisheries and aquaculture in Africa as a repository within AU institutions and establish a mechanism for regular updating; | 1.1.1.1. Develop and update database on fisheries and aquaculture and develop mechanism for data management. | Database development and mechanism for updating is ongoing by Centre of Excellence: Department of Fisheries and aquatic sciences (DFAS), University of Cape Coast, Ghana
 | 1.1.1.2. Commission studies on identifications of sources of fisheries, aquaculture, socio-economics and environmental related data (research and statistics) in 2 regions. | The request for proposal was sent to COEs and other knowledge-based institutions. Submitted applications were not successful. The TORS has ben revised and the RFP is being shared again.
1.1.2. Conduct policy oriented studies to address social, economic and environmental challenges on fisheries and aquaculture in Africa (e.g. on the state of the stocks, economic valuation of aquatic and coastal goods and services, impact of climate change etc). | 1.1.2.1. Collect existing relevant information in AU MS and institutions on the state of fish stocks in 2 regions. | AUDA
 | 1.1.2.2. Conduct economic valuation of ecosystem goods and services, impact of climate change on fisheries and aquaculture. | AUDA
1.1.3. Update the AU-FAO study on the Value of African fisheries (2014); | 1.1.3.1. Develop methodology, template and training manuals for updating the AU-FAO study on the value of fisheries 2014. | AUDA
1.1.4. Produce foresight studies and relevant fisheries and aquaculture contributions to ongoing thematic processes and initiatives (i.e. on food and nutrition security, gender, marine biodiversity and ecosystems, climate change, blue economy etc) | 1.1.4.1 Conduct foresight studies to inform policy reforms on relevant fisheries and aquaculture issues - diverse consultancies to address issues above. | AUDA
1.1.5. Document lessons learnt and best practices for informed and rational interventions; | 1.1.5.1. Document lessons learnt and best practices on current and emerging fisheries and aquaculture related issues for informed and rational interventions. | The request for proposal has been developed and is being shared with the Centres of excellence and other knowledge-based institutions

## Slide 3: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.2 Existing platforms and networks are reviewed, rationalized and operationalized for effective participation of stakeholders in policy development and implementation |  | 
1.2.1. Conduct a functional review of existing platforms and networks in relation to PFRS and AFRM (e.g. AFRIPAAS, AWFISHNET, Policy Research Network etc); | 1.2.1.1. Review and propose mechanisms for rationalization of existing fisheries and aquaculture platforms and networks and propose a framework for anchorage with RECs and relevant RFOs. | The review and development of mechanism for rationalization of existing networks and platforms is going by the Centre of excellence
1.2.2. Support rationalization of existing platforms and networks, ensure institutional anchorage at relevant level, enhance their capacities and use them to implement identified activities / pilot projects; | 1.2.2.1. Conduct workshops to train rationalized platforms/networks to operationalize anchorage and enhance capacities on implementation of approved workplans and policy. | Following establishment of regional NSA platforms, the continental coordinating platform for NSAs established platform. This ongoing study in 1.2.1 will propose a mechanism for anchorage with regional and continental organizations. The NSAs and women networks have ben utilized in common position development in global e.g. Ministerial conference of Organization of Africa, Caribbean and Pacific States in April 2022. An inventory of NSAs and networks is ongoing by COE
 | 1.2.2.2. Purchase equipment as may be required by COEs or other specialized institutions for effective implementation of activities related to the Action. | The process is ongoing
 | 1.2.2.3 Conduct assessment and review for selection of additional centres of excellence in relevant disciplines in fisheries and aquaculture; | Assessment is planned for Angola and Namibia for assessment of two institutions
1.2.3 Develop cost effective mechanisms for stakeholder consultation. | 1.2.3.1 Commission a study to develop a cost effective mechanism for stakeholder's consultation and generate specific recommendations based on best practices. | The study has been commissioned and cost effective mechanism is being developed by COE for stakeholders consultation.
1.2.4. Simplify and operationalize the AFRM. | 1.2.4.1. Organize a consultative workshop to revise TORs for the various organs of the AFRM in line with the third STC-ARDWE recommendation. | The revised African Fisheries Reform Mechanism (AFRM) was operationalized in August 2021; the associated organs, including four working groups, Think Tank executive committee and advisory council have been reconstituted and operationalized. through consultative processes.

## Slide 4: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.3 A solid reporting system to STC on the implementation of the PFRS is put in place and integrated to CAADP process. |  | Progress of Implementation
1.3.1. Develop indicators to monitor the implementation of PFRS in line with the Malabo goals. | 1.3.1.1 Develop and propose mechanisms for operationalization of a robust M&E systems based on PFRS guidelines for monitoring PFRS implementation. | Expert consultative meeting organized in April 2022 and indicators developed consistent with PFRS Guidelines and aligned to indicators for monitoring implementation of Malabo Goals
1.3.2. Produce annual snapshot of fisheries and aquaculture performance reports based on these indicators | 1.3.2.1. Prepare and compile biennial status report that would contribute to the Africa fisheries and aquaculture report for year 1 | Terms of reference developed for RFPs from COEs.
1.3.4. Actively contribute to the agenda of STC meetings, based on strategic planning and support the organization of biennial African ministerial dialogue on Fisheries and aquaculture. | 1.3.4.2 Prepare documentations for 3 STCs and high level AU policy organs. | The documentations were developed for STC-ARDWE in 2021; i.Continental Inland fisheries strategy ii. Enhancing PP in fisheries and aquaculture iii. Harmonized minimum conditions for access iv. Draft terms of reference for sectoral committee on fisheries and aquaculture. They were not submitted last year but will be submitted for the STC-ARDWE in 2022.
 | 1.3.4.3. Facilitate the participation of experts in STC expert session's meetings to develop recommendations for the STC-ARDWE. | compiled list of experts (Directors of fisheries and aquaculture ) in AU member states and submitted to 2021 STC-ARDWE organizing committee; the meeting was held virtually
 | 1.3.4.4. Facilitate the participation of relevant officials in STC ministerial sessions to, among others, review the experts' recommendations. | Compiled list of Ministers in charge of fisheries and aquaculture in AU member states for the 2021 STC-ARDWE meeting (held virtually)
Output 1.4 Mechanisms are developed to ensure that sustainable fisheries and aquaculture are mainstreamed in the development of AU policies / initiatives affecting the sector. |  | 
1.4.1. Map initiatives that are underway or planned at the AU that are relevant to fisheries and aquaculture and contribute to their development / implementation by providing relevant input (of. discussions on blue economy, maritime security, environmental protection and oceangovernance etc). Build synergies and support alignment among these different sectors; | 1.4.1.1. Organize internal virtual meeting among AUC Departments to map initiatives that are underway or planned at the AU which are relevant to fisheries and aquaculture, for synergistic implementation of activities that relevant to fisheries and aquaculture (e.g. blue economy, maritime security, environmental protection and ocean governance) | Internal coordination meeting among AUC Departments will be organized this week to map ongoing initiatives relevant to fisheries and aquaculture to build synergies and coordination
1.4.3. Associate relevant AU services to activities developed under this Action | 1.4.3.1. Organize internal virtual (and Physical meetings) to develop and operationalize a framework for internal coordination of fisheries and aquaculture among relevant AUC Actors | Internal coordination meeting among AUC Departments will be organized this week to internal coordination mechanism among AUC departments

## Slide 5: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.1 Capacities and systems for regional collaboration and integration regarding shared fisheries and aquaculture resources management are improved and linkages with environmental governance frameworks are enhanced. |  | Progress of implementation
2.1.1. Facilitate coordination among regional organizations (RECs, RFB and RSC) through regular exchange of information between the APRIFAAS members. | 2.1.1.1.Conduct bi-annual consultative meetings to exchange information, review and align workplans within the framework of AFRM for synergistic implementation and enhanced coordination. | Two consultative meetings for regional institutions in fisheries, aquaculture and other aquatic systems organized
2.1.2. Ensure cross-regional/trans-regional coherence of RECs and RFBs strategies and facilitate their institutional anchorage, in line with the PFRS. | 2.1.2.1. Collect best practices and lessons learnt on functional institutional anchorage between RECs and RFBs/RSC and propose a framework for effective anchorage. | Studies ongoing by COE to collate lessons and best practices on institutional anchorage
2.1.3. Identify mechanisms for establishing / strengthening linkages between regional organizations in charge of fisheries management (RFMOs/RFBs) and regional organizations in charge of environmental issues (RSC and inland water bodies). | 2.1.3.1. Develop a mechanism for establishing/strengthening linkages between specialized regional fisheries institutions and environmental agencies. | Stakeholder’s workshop will be organized to validate the finds of the above studies (2.1.2.1)
Output 2.2 Capacities of Member States, RECs and RFBs to develop realistic sustainable fisheries and aquaculture policies in coherence with the PFRS are strengthened. |  | Progress of implementation
2.2.1. Develop capacities and provide technical support to Member states and RECs to develop sectoral strategies and investment plans | 2.2.1.1. Conduct studies to establish which AU MS have sectoral strategies and investment plans and develop a mechanism for twinning between those with and those without – 5 regions | AUDA
2.2.2. Support member States in reviewing their policies and legislations and aligning them with best international practices (i.e. the FAO code of conduct for responsible Fisheries, etc) and existing continental / regional instruments (e.g. PRFS, RFB/RSC recommendations etc) | 2,2,2,1 Review and align national fisheries and aquaculture polices and laws with the PFRS, regional instruments and global best practices for 15 AU member states | Studies ongoing by COE to review and align national fisheries and aquaculture polices and laws with the PFRS, regional instruments and global best practices for 15 AU member states
 | 2.2.2.2. Facilitate national validation workshop for reviewed national policies and laws at Member States’ level. | Validation workshop will be conducted after the review of national policies
2.2.3. Mainstream sustainable and climate-resilient fisheries and aquaculture in NAIPS, RAIPs and other Investment programmes. | 2.2.3.1. Review national and regional fisheries-aquaculture plans to mainstream sustainable and climate-resilient, environmentally sustainable fisheries and aquaculture, in NAIPS, RAIPs and other Investment programmes. | The terms of reference for request for proposals from the Centres of Excellence has been developed
 | 2.2.3.2 Conduct national consultative workshops to validate the outcomes of the above review in 15 AU member states | The national consultative workshops will be organized after the studies in 2.2.3.1.
 | 2.2.3.3. Conduct regional consultative workshops to validate the outcomes of the above review (5 RECs). | The regional consultative workshops will be organized after the studies in 2.2.3.1.
2.2.4. Facilitate stakeholders consultation on the design and implementation of national and regional strategies | 2.2.4.1. Develop training materials and facilitate a training workshop on the design of fisheries and aquaculture strategies for implementation at national and regional levels. | The activity will be conducted after the studies 2.2.3.1

## Slide 6: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.3 Capacities are strengthened to facilitate intra and inter regional fish trade in line with the regional integration trade agenda and the Protocol on Trade in Goods of the Africa Continental Free Trade Area |  | 
2.3.1. Identify strategic regional value chains for sustainable fisheries and aquaculture | 2.3.1.1 Hire 3 COEs to conduct studies in West_Central, East_Southern and Northern regions to identify strategic regional value chains for sustainable fisheries and aquaculture | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy
2.3.3. Support regional approaches for the establishment of regional reference laboratories and diagnostic networks; | 2.3.3.1. Conduct institutional assessment of laboratories and diagnostics networks in the various regions of Africa and recommend mechanisms for establishing regional reference laboratories and diagnostic networks for fish and fish products. The consultancy should also entail assessment of capacities for other certification processes for enhanced market access. | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy
2.3.4. Enhance the capacity of fisheries and aquaculture traders with due consideration for small scale traders and women engaged in fish trade an processing; | 2.3.4.1. Develop an advocacy strategy and mechanism for effective participation of women and youth fish traders in fisheries and aquaculture policy dialogue and networking. | AUDA
 | 2.3.4.3. Organize national workshops to facilitate establishment of national chapters for Awfishnet in fragile states (15 AU MS) towards strengthening effective engagement in decision making at national levels on issues relating to fisheries and aquaculture. | 15 national chapters of Awfishnet have been established: Egypt, Mauritania, South Sudan, Sierra Leone, South Africa, Zambia, Chad, Gabon, Niger, Liberia, Kenya,
2.3.5. Improve aquatic disease outbreak detection, notification and support coordinated response. | 2.3.5.1.Develop Guidelines to strengthen diagnostic capacities of competent national authorities and networks on aquatic animal disease detection, surveillance and coordinated responses, based on OIE Aquatic Animal Health Code and Manual of Diagnostic Tests for Aquatic Animals (this activity includes stakeholder's participation in a virtual meeting to validate the guidelines). | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy

## Slide 7: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
Output 3.1 Capacities of AU Member States – including SIDS - in terms of international negotiations are increased and a mechanism is put in place to coordinate African common positions. |  | Progress of implementation
3.1.2. Identify specific needs of African SIDS and take them into account in strategic positions in international fora | 3.1.1.1. Convene annual expert's meetings to identify specific and emerging issues and draft common positions for deliberation and adoption at relevant fora. | Expert meeting planned and scheduled for August in Seychelles 2022
 | 3.1.2.1. Identify specific issues relevant to SIDs and develop draft strategic positions and make specific recommendations for establishment/strengthening a platform of SIDS. | Studies ongoing by COEs
 | 3.1.2.2 Convene a virtual consultative workshop to validate draft strategic position and the recommendations for establishment of a platform of SIDs. | Virtual meeting will be convened after 3.1.1.1 and 3
3.1.3. Identify expertise in the different Member States and set up a consultation mechanism to prepare positions; | 3.1.3.1.Prepare a roster of fishery and aquaculture experts in the different Member States and set up a consultation mechanism to draft positions and mobilize technical expertise | Terms of reference developed for launching call for proposals from COES
 | 3.1.3.2. Conduct a virtual workshop involving AU member states on identification of issues and formulation of common positions. | To be conducted after 3.1.3.1
3.1.4. Increase capacities on international issues and organize specific trainings for pre-identified negotiators; | 3.1.4.1. Identify global issues and agendas which impact on national, regional and continental fisheries and aquaculture development. | Terms of reference developed for launching call for proposals from COES
 | 3.1.4.2. Conduct an expert consultative training workshop on negotiation skills. | To be undertaken
 | 3.1.4.3. Present and advocate for African common positions at relevant fora. | Supported African stakeholders (AU MS, NSAs etc) to OACPS in Ghana, World aquaculture society in Alexandria, Lisbon Ocean conference in Portugal
3.1.5. Prepare African common positions using AU processes; | 3.1.5.1. Convene side events with the African Group of ambassadors and negotiators to agree on African common positions to be presented at relevant fora. | To be undertaken
3.1.6. Assist AU policy organs in the identification and participation of African champions (HSG and Ministers) in relevant High level events, enhancing visibility of the African voice | 3.1.6.1. Assist AU policy organs representatives to attend relevant high level events to enhance visibility of African fisheries and aquaculture. | AUDA

## Slide 8: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 3.2 Mechanisms are put in place to encourage and facilitate the domestication of global instruments and initiatives at continental, regional and national levels |  | 
3.2.1. Identify a list of priority instruments and initiatives (e.g. PSMA, CCRF, SSF-VG, CITES, CBD etc) | 3.2.1.1. Identify and analyze priority instruments and initiatives and outline strategies for effective participation by AU member states. | COE recruited and the study is ongoing
3.2.2. Establish and regularly update their state of ratification and domestication | 3.2.2.1. Develop a mechanism for follow-up on implementation and ratification of relevant instruments by AU MS for biennial reporting progress of domestication, including instruments relating to combating IUU (eg PSMA, EU-IUU regulations). | COE recruited and the study is ongoing
 | 3.2.2.3. Convene a virtual consultative meeting with AU MS and RECs to validate. | Will take place after the studies
 | 3.2.2.4. Conduct a review of national policies in 15 AU MS and make specific recommendations for alignment and domestication of global instruments. | RFP developed and will be launched
3.2.3. Develop inputs for the STCs and high level AU policy organs | 3.2.3.1. Prepare meeting documents for STC and high level AU Policy Organs; STC meetings thrice in 4 years (AU-IBAR, AUDA-NEPAD, DREA). | Meeting documents developed for last STC
 | 3.2.3.2. Organize internal meetings to prepare issues for presentation to STCs and other High Level Policy meetings: (AU-IBAR, DREA, OLC (AU office of Legal Counsel) and other relevant AUC departments and STC-ARDWE Bureau; | Internal meetings with AUC departments will take place this week
3.2.4. Support dialogue and sensitization at RECs level | 3.2.4.1 Convene regular dialogue meetings and sensitization with RECs on emerging issues of the Action. | First dialogue meeting with RECs held last year
3.2.5. Identify mechanisms supporting developing countries’ involvement and compliance and promote their use by AU member States | 3.2.5.1.Establish and operationalize a biennial forum for regular consultations on monitoring compliance on domestications of global and continental instruments within the framework of AFRM. | Consultative workshop organized and biennial forum establshed
3.3.1. Collect information on relevant EU initiatives (Alliance for Sustainable Investment and Jobs, EIP etc); | 3.3.1.1. Prepare materials on relevant EU initiatives and make appropriate recommendations to AU MS for articulation of coherent African positions during AU-EU dialogue. | In progress
3.3.2. Engage in a regular sectoral dialogue with European Commission services and identify issues of common interest; | 3.3.2.1. Organize virtual dialogue meetings with EU (once a year) to identify issues of common interest in fisheries and aquaculture. | in progress

## Slide 9: EMERGING ISSUES

## Slide 10: Thank You
AU-IBAR: Providing leadership in the development of animal resources for Africa