## Slide 1: SECOND DIALOGUE AND SENSITIZATION MEETING WITH RECS ON EMERGING ISSUES FROM IMPLEMENTATION OF FISHGOV-2
PROGRESS OF IMPLEMENTATION
Enhancing sustainable fisheries management and aquaculture development in Africa: A programme for accelerated reform of the sector (FishGov-2)
13-15 June 2022
ABUJA, NIGERIA

## Slide 2: PROJECT INCEPTION PHASE APRIL-MAY 2021
Output | Activity | Progress of implementation
Project Technical Coordinating Committee meeting (PTCC) | Organize Project technical coordination meeting | Two PTCC meetings held; one in April 2021 (virtual) and one in December 2021 (physical)
Project Steering Committee meeting (PSC) | Organize first project steering committee meeting | First PSC meeting held in April 2021 (Virtual)
Inception meeting | Organize project inception meeting | Inception meeting held inn may 2021 (virtual)

## Slide 3: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output | Activity | Progress of implementation
Output 1 1: AU stakeholders have access to quality knowledge products on African fisheries and aquaculture |  | 
1.1:1. Collect and centralize information and research relating to fisheries and aquaculture in Africa as a repository | 1.1.1.1. Develop and update database on fisheries and aquaculture and develop mechanism for data management. | Database development and mechanism for updating is ongoing by COE: DFAS, UCC, Ghana
 | 1.1.1.2. Commission studies on identifications of sources of fisheries, aquaculture, socio-economics and environmental related data (research and statistics) in regions. | The request for proposal was sent to COEs but applications not successful. The TORS have been revised and process is on
1.1.2. Conduct policy-oriented studies to address socio- economic and environmental challenges on fisheries and aquaculture in Africa (e.g. on the state of the stocks, economic valuation of aquatic and coastal goods and services, impact of climate change etc). | 1.1.2.1. Collect existing relevant information in AU MS and institutions on the state of fish stocks in 5 African regions | Terms of reference being developed for launching call for proposals from COES
 | 1.1.2.2. Conduct economic valuation of ecosystem goods and services, impact of climate change on fisheries and aquaculture. | Terms of reference being developed for launching call for proposals from COES

## Slide 4: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output | Activity | Progress of implementation
Output 1 1: AU stakeholders have access to quality knowledge products on African fisheries and aquaculture |  | 
1.1.3. Update the AU-FAO study on the Value of African fisheries (2014); | 1.1.3.1. Develop methodology, template and training manuals for updating the AU-FAO study on the value of fisheries 2014. | Will be implemented jointly with FAO; AUDA takes the lead
1.1.4. Produce foresight studies and relevant fisheries and aquaculture contributions to ongoing thematic processes and initiatives (i.e. on food and nutrition security, gender, marine biodiversity and ecosystems, climate change, blue economy accountingetc) | 1.1.4.1 Conduct foresight studies to inform policy reforms on relevant fisheries and aquaculture issues - diverse consultancies to address issues above. | Terms of reference being developed for launching call for proposals from COES
1.1.5. Document lessons learnt and best practices for informed and rational interventions; | 1.1.5.1. Document lessons learnt and best practices on current and emerging fisheries and aquaculture related issues for informed and rational interventions. | The request for proposal has been developed and in the process of being shared with the COEs

## Slide 5: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.2 Existing platforms and networks are reviewed, rationalized and operationalized for effective participation of stakeholders in policy development and implementation |  | 
1.2.1. Conduct a functional review of existing platforms and networks in relation to PFRS and AFRM (e.g. AFRIPAAS, AWFISHNET, Policy Research Network etc); | 1.2.1.1. Review and propose mechanisms for rationalization of existing fisheries and aquaculture platforms and networks and propose a framework for anchorage with RECs and relevant RFOs. | The consultancy review and development of mechanism for rationalization of existing networks and platforms awarded to the COE; The national Fisheries resources research institute (NaFIRRI), Uganda. An inventory of NSAs and networks will also be conducted by the COE for updating existing information.
1.2.2. Support rationalization of existing platforms and networks, ensure institutional anchorage at relevant level, enhance their capacities and use them to implement identified activities / pilot projects; | 1.2.2.1. Conduct workshops to train rationalized platforms/networks to operationalize anchorage and enhance capacities on implementation of approved workplans and policy. | A continental coordinating platform for NSA established. This ongoing study in 1.2.1 will propose a mechanism for anchorage with regional and continental organizations. The continental NSAs and women networks have bee involved in utilized in common position development in global e.g. Ministerial conference of OACPS in April 2022.
 | 1.2.2.2. Purchase equipment as may be required by COEs for effective implementation of activities related to the Action. | The process is ongoing; the COEs have been requested to identify suppliers.
 | 1.2.2.3 Conduct assessment and review for selection of additional centres of excellence in relevant disciplines in fisheries and aquaculture; | Assessment is planned for two institutions in Angola and Namibia;

## Slide 6: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.2 Existing platforms and networks are reviewed, rationalized and operationalized for effective participation of stakeholders in policy development and implementation |  | 
1.2.3 Develop cost effective mechanisms for stakeholder consultation. | 1.2.3.1 Commission a study to develop a cost-effective mechanism for stakeholder's consultation and generate specific recommendations based on best practices. | The consultancy has been awarded to NAFIRRI
1.2.4. Simplify and operationalize the AFRM. | 1.2.4.1. Organize a consultative workshop to revise TORs for the various organs of the AFRM in line with the third STC-ARDWE recommendation. | The revised African Fisheries Reform Mechanism (AFRM) was operationalized in August 2021; the associated organs, including four working groups, Think Tank executive committee and advisory council have been reconstituted and operationalized through consultative processes.

## Slide 7: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.3 A solid reporting system to STC on the implementation of the PFRS is put in place and integrated to CAADP process |  | Progress of Implementation
1.3.1. Develop indicators to monitor the implementation of PFRS in line with the Malabo goals. | 1.3.1.1 Develop and propose mechanisms for operationalization of a robust M&E systems based on PFRS guidelines for monitoring PFRS implementation. | Expert consultative meeting organized in April 2022 and indicators developed consistent with PFRS Guidelines and aligned to indicators for monitoring implementation of Malabo Goals
1.3.2. Produce annual snapshot of fisheries and aquaculture performance reports based on these indicators 1.3.3. Contribute to the biennial review of Malabo goals for monitoring progress of implementation of AU decisions; | 1.3.2.1. Prepare and compile biennial status report that would contribute to the Africa fisheries and aquaculture report for year 1 Facilitate the participation of national, regional representatives and AFRM experts in CAADP biennial review processes to integrate fisheries and aquaculture in thebiennial CAADP report on Malabo Goals and targets. | Terms of reference developed for RFPs from COEs in process Supported the participation of experts in 3rd CAADP biennial review process to integrate fisheries and aquaculture. A knowledge product was also finalized to mainstream fisheries and aquaculture indicators on the overall CAADP process.

## Slide 8: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.3 A solid reporting system to STC on the implementation of the PFRS is put in place and integrated to CAADP process |  | Progress of Implementation
1.3.4. Actively contribute to the agenda of STC meetings, based on strategic planning and support the organization of biennial African ministerial dialogue on Fisheries and aquaculture. | 1.3.4.2 Prepare documentations for 3 STCs and high-level AU policy organs. | The documentations were developed for STC-ARDWE in 2021; I. Continental Inland fisheries strategy ii. Enhancing PP in fisheries and aquaculture iii. Harmonized minimum conditions for access iv. Draft terms of reference for sectoral committee on fisheries and aquaculture. They were not submitted last year but will be submitted for the STC-ARDWE in 2022.
 | 1.3.4.3. Facilitate the participation of experts in STC expert session's meetings to develop recommendations for the STC-ARDWE. | Compiled list of experts (Directors of fisheries and aquaculture ) in AU member states and submitted to 2021 STC-ARDWE organizing committee; the meeting was held virtually
 | 1.3.4.4. Facilitate the participation of relevant officials in STC ministerial sessions to, among others, review the experts' recommendations. | Compiled list of Ministers in charge of fisheries and aquaculture in AU member states for the 2021 STC-ARDWE meeting (held virtually)

## Slide 9: SO1: African Union decisions on sustainable fisheries and aquaculture policies are evidence based.
Output 1.4 Mechanisms are developed to ensure that sustainable fisheries and aquaculture are mainstreamed in the development of AU policies / initiatives affecting the sector. |  | Progress of implementation
1.4.1. Map initiatives that are underway or planned at the AU that are relevant to fisheries and aquaculture and contribute to their development / | 1.4.1.1. Organize internal virtual meeting among AUC Departments to map initiatives that are underway or planned at the AU which are relevant to fisheries and aquaculture, | Internal coordination meeting among AUC Departments will be organized this week to map ongoing initiatives relevant to fisheries and aquaculture to build synergies and coordination
1.4.2. Engage with non-fisheries and aquaculture actors (e.g. ministers in charge of finance, trade, planning, financial institutions etc); | 1.4.2.1. Create awareness among relevant non-fisheries and aquaculture decision makers to stimulate in-country investments in fisheries and aquaculture . | Awareness enhancing and sensitization meeting organized involving depts. In charge of development, finance, trade and industry, environment including representatives of RECS, fisheries department
1.4.3. Associate relevant AU services to activities developed under this Action | 1.4.3.1. Organize internal virtual (and Physical meetings) to develop and operationalize a framework for internal coordination of fisheries and aquaculture among relevant AUC Actors | Internal coordination meeting among AUC Departments will be organized this week to internal coordination mechanism among AUC departments

## Slide 10: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.2 Capacities of Member States, RECs and RFBs to develop realistic sustainable fisheries and aquaculture policies in coherence with the PFRS are strengthened. |  | Progress of implementation
2.2.1. Develop capacities and provide technical support to Member states and RECs to develop sectoral strategies and investment plans | 2.2.1.1. Conduct studies to establish which AU MS have sectoral strategies and investment plans and develop a mechanism for twinning between those with and those without – 5 regions | Terms of reference developed for launching call for proposals from COES
2.2.2. Support member States in reviewing their policies and legislations and aligning them with best international practices | 2,2,2,1 Review and align national fisheries and aquaculture polices and laws with the PFRS, regional instruments and global best practices for 15 AU member states | Contract awarded to ACECOR (Africa Centre of Excellence in Coastal Resilience, UCC, Ghana)

## Slide 11: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.3 Capacities are strengthened to facilitate intra and inter regional fish trade in line with the regional integration trade agenda and the Protocol on Trade in Goods of the Africa Continental Free Trade Area |  | Progress of implementation
2.3.1. Identify strategic regional value chains for sustainable fisheries and aquaculture | 2.3.1.1 Hire 3 COEs to conduct studies in West_Central, East_Southern and Northern regions to identify strategic regional value chains for sustainable fisheries and aquaculture | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy; draft subdelegation agreement developed regarding transfer of funds
2.3.2. Support RECs and their Member States in reviewing their trade and SPS policies to facilitate fish trade along those strategic regional value chains; | 2.3.2.1Consultancy by OIE | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy; draft subdelegation agreement developed regarding transfer of funds
2.3.3. Support regional approaches for the establishment of regional reference laboratories and diagnostic networks; | 2.3.3.1. Conduct institutional assessment of laboratories and diagnostics networks in the various regions of Africa and recommend mechanisms for establishing regional reference laboratories and diagnostic networks for fish and fish products. | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy; draft subdelegation agreement developed regarding transfer of funds

## Slide 12: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.3 Capacities are strengthened to facilitate intra and inter regional fish trade in line with the regional integration trade agenda and the Protocol on Trade in Goods of the Africa Continental Free Trade Area |  | Progress of implementation
2.3.4. Enhance the capacity of fisheries and aquaculture traders with due consideration for small scale traders and women engaged in fish trade an processing; | 2.3.4.1. Develop an advocacy strategy and mechanism for effective participation of women and youth fish traders in fisheries and aquaculture policy dialogue and networking. | Terms of reference being developed for launching call for proposals from COES
 | 2.3.4.2. Train members of the African women fish processors and traders network (AWfishNet) on policy dialogue, governance, leadership, advocacy, effective networking, communication and organizational skills. | Traning will be conducted after the advocacy strategy and mechanism developed

## Slide 13: SO2 Fisheries and aquaculture policies in Africa are coherent with the PFRS and coordinated at continental, regional and national levels in order to maintain healthy and resilient marine, coastal and freshwater ecosystems in the context of climate change.
Output 2.3 Capacities are strengthened to facilitate intra and inter regional fish trade in line with the regional integration trade agenda and the Protocol on Trade in Goods of the Africa Continental Free Trade Area |  | Progress of implementation
 | 2.3.4.3. Organize national workshops to facilitate establishment of national chapters for Awfishnet in fragile states (15 AU MS) towards strengthening effective engagement in decision making at national levels on issues relating to fisheries and aquaculture. | 15 national chapters of Awfishnet have been established: Egypt, Mauritania, South Sudan, Sierra Leone, South Africa, Zambia, Chad, Gabon, Liberia, Kenya,, Ethiopia, CAR, Malawi, Cote D’Ivoire, Tunisia
2.3.5. Improve aquatic disease outbreak detection, notification and support coordinated response. | 2.3.5.1.Develop Guidelines to strengthen diagnostic capacities of competent national authorities and networks on aquatic animal disease detection, surveillance and coordinated responses, based on OIE Aquatic Animal Health Code and Manual of Diagnostic Tests for Aquatic Animals (this activity includes stakeholder's participation in a virtual meeting to validate the guidelines). | Consultations with OIE concluded and preparations by OIE are in progress for implementation of this consultancy; draft subdelegation agreement developed regarding transfer of fund

## Slide 14: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
Output 3.1 Capacities of AU Member States – including SIDS - in terms of international negotiations are increased and a mechanism is put in place to coordinate African common positions. |  | Progress of implementation
3.1.2. Identify specific needs of African SIDS and take them into account in strategic positions in international fora | 3.1.1.1. Convene annual expert's meetings to identify specific and emerging issues and draft common positions for deliberation and adoption at relevant fora. | Expert meeting planned and scheduled for August in Seychelles 2022
 | 3.1.2.1. Identify specific issues relevant to SIDs and develop draft strategic positions and make specific recommendations for establishment/strengthening a platform of SIDS. | Contract awarded to ACECOR
3.1.3. Identify expertise in the different Member States and set up a consultation mechanism to prepare positions; | 3.1.3.1.Prepare a roster of fishery and aquaculture experts in the different Member States and set up a consultation mechanism to draft positions and mobilize technical expertise | Terms of reference developed for launching call for proposals from COES

## Slide 15: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
Output 3.1 Capacities of AU Member States – including SIDS - in terms of international negotiations are increased and a mechanism is put in place to coordinate African common positions. |  | Progress of implementation
3.1.4. Increase capacities on international issues and organize specific trainings for pre-identified negotiators; | 3.1.4.1. Identify global issues and agendas which impact on national, regional and continental fisheries and aquaculture development. | Terms of reference developed for launching call for proposals from COES
 | 3.1.4.2. Conduct an expert consultative training workshop on negotiation skills. | To be undertaken
 | 3.1.4.3. Present and advocate for African common positions at relevant fora. | Supported African stakeholders (AU MS, NSAs etc) to OACPS in Ghana, World aquaculture society in Alexandria, Lisbon Ocean conference in Portugal

## Slide 16: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
Output 3.1 Capacities of AU Member States – including SIDS - in terms of international negotiations are increased and a mechanism is put in place to coordinate African common positions. |  | Progress of implementation
3.1.5. Prepare African common positions using AU processes; | 3.1.5.1. Convene side events with the African Group of ambassadors and negotiators to agree on African common positions to be presented at relevant fora. | AUDA-NEPAD supported the African Regional Group of Ambassadors to the Rome-based agencies to formulate common African positions for submission to the 34th Session of COFI. The project supported the development of a total of twelve common position statements that were delivered by representatives of the ARG during the relevant sessions.
3.1.6. Assist AU policy organs in the identification and participation of African champions (HSG and Ministers) in relevant High-level events, enhancing visibility of the African voice | 3.1.6.1. Assist AU policy organs representatives to attend relevant high-level events to enhance visibility of African fisheries and aquaculture. | Plan to assist AU policy organs representatives to attend COFI35.

## Slide 17: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
Output 3.2 Mechanisms are put in place to encourage and facilitate the domestication of global instruments and initiatives at continental, regional and national levels |  | Progress of implementation
3.2.1. Identify a list of priority instruments and initiatives | 3.2.1.1. Identify and analyze priority instruments and initiatives and outline strategies for effective participation by AU member states. | Contract awarded to ACECOR
3.2.2. Establish and regularly update their state of ratification and domestication | 3.2.2.1. Develop a mechanism for follow-up on implementation and ratification of relevant instruments by AU MS for biennial reporting progress of domestication, | Contract awarded to ACECOR
 | 3.2.2.4. Conduct a review of national policies in 15 AU MS and make specific recommendations for alignment and domestication of global instruments. | TORs developed and RFP to COEs in process
3.2.3. Develop inputs for the STCs and high-level AU policy organs | 3.2.3.1. Prepare meeting documents for STC and high level AU Policy Organs; STC meetings thrice in 4 years (AU-IBAR, AUDA-NEPAD, DREA). | Meeting documents developed for last STC
 | 3.2.3.2. Organize internal meetings to prepare issues for presentation to STCs and other High Level Policy meetings: (AU-IBAR, DREA, OLC (AU office of Legal Counsel) and other relevant AUC departments and STC-ARDWE Bureau; | Internal meetings with AUC departments will take place this week

## Slide 18: SO3. Africa is adequately represented and effectively participates in international fisheries and aquaculture fora and ably domesticates relevant global instruments.
3.2.4. Support dialogue and sensitization at RECs level | 3.2.4.1 Convene regular dialogue meetings and sensitization with RECs on emerging issues of the Action. | First dialogue meeting with RECs held last year and developed proposals for mechanisms for dialogue
3.2.5. Identify mechanisms supporting developing countries’ involvement and compliance and promote their use by AU member States | 3.2.5.1.Establish and operationalize a biennial forum for regular consultations on monitoring compliance on domestications of global and continental instruments within the framework of AFRM. | Stakeholders consultative workshop organized and biennial forum established IN March 2022, Tanzania
3.3.1. Collect information on relevant EU initiatives (Alliance for Sustainable Investment and Jobs, EU Innovative partnerships (EIP) etc); | 3.3.1.1. Prepare materials on relevant EU initiatives and make appropriate recommendations to AU MS for articulation of coherent African positions during AU-EU dialogue. | In progress by the Legal expert
3.3.2. Engage in a regular sectoral dialogue with European Commission services and identify issues of common interest; | 3.3.2.1. Organize virtual dialogue meetings with EU (once a year) to identify issues of common interest in fisheries and aquaculture. | in progress

## Slide 19: Planned activities – June to December 2022
No. | Title of activities | Dates | comments
1 | Dialogue with RECs | June | This week
2 | AUC Internal coordination | June | This week
3 | Training on ocean governance and fisheries access arrangements | June | 
4 | COEs – cost of consultancies awarded (committed funds) | July | Committed funds
5 | COEs – cost of consultancies in process of been awarded | July | This includes consultancies under AUDA also,
6 | Ocean governance conference, Lisbon | June-July | African Common positions
7 | Training on fish cage culture and environmental governance | July | 
8 | Development of indicator handbook for monitoring PFRS and mainstreaming fin AUC BR (Biennial review) process | July | 
9 | Aquatic animal health activities to be implemented by OIE | July-August | Sub delegation agreement being developed
10 | Establishing or strengthening platform for SIDs for effective common positions | August | 
11 | 5th General assembly meeting of APRIFAAS | October | 
12 | AFRM Advisory council meeting and aquaculture working group | October | 
13 | Third Project technical coordination meeting | November | 
14 | Second project steering committee meeting | November | 
15 | Audit |  | 
16 | Project evaluation |  | 
17 | Anticipated missions (by staff) |  | 
18 | Purchase of equipment for 4 COEs |  | 

## Slide 20: EMERGING ISSUES
Food security crisis on the continent due to the ongoing situation of the Russia-Ukraine war, how can the fisheries and aquaculture sector can contribute to address this emerging issue?- through FishGov 2 activities
Series of requests from AU member states and RECs for support (most often outside the project domain); how can these be accommodated e.g. to build market stalls; to provide fish preservation facilities for women; how can we handle this?
Protracted consultancies have contracted to delay in project implementation. Expert consultative meetings would results in quick expected results for some consultancies; the expertise of the WGs can be utilized. This approach was adopted successfully during FishGov 1 presentation
Increasing on project to promote African common voice and effective participation in Global for a.
Partnership has been strengthened with institutions like FAO, OIE, AFDB
Common African positions on global fora and integrating NSAs in the process; increasing support here

## Slide 21: CHALLENGES AND WAY FORWARD
1. Challenges
  Delays on the preparation and launch of the numerous studies of the project.
  Slow recruitment process for fixed project staff
1I. Way Forward
  Continue to support African Member States in speaking with one voice in global fora.
  Expert consultative process

## Slide 22: Thank You
AU-IBAR: Providing leadership in the development of animal resources for Africa